## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE-Automated Resume Builder | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Computer Science and Engineering-Data Science )
PROJECT GUIDE- Prof. Anagha Aher | [6 empty] | DATE | [6 empty] | 2022-10-11
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Sanskruti Chavan Janhavi Kasar DalbirSingh Matharu Mayank Kumar | 2022-07-26 | 2022-08-03 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | DalbirSingh Matharu Mayank Kumar | 2022-08-10 | 2022-08-16 | 1 | 100% | bar: WEEK 3 M to WEEK 5 F
1.3 | Discussing the project topic with the help of paper prototype. | Sanskruti Chavan Janhavi Kasar | 2022-08-16 | 2022-08-23 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F
1.4 | Designing the Graphical User Interface(GUI) | Sanskruti Chavan Janhavi Kasar DalbirSingh Matharu Mayank Kumar | 2022-08-23 | 2022-09-13 | 3 | 100% | bar: WEEK 7 M to WEEK 8 F
1.5 | Presentation I | Sanskruti Chavan Janhavi Kasar Mayank Kumar | 2022-09-19 | 2022-09-23 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
2 | Project Design and Implementation
2.1 | Database Design | DalbirSingh Matharu | 2022-09-20 | 2022-09-27 | 1 | 100% | bar: WEEK 10 M to WEEK 10 F
2.2 | Database Connectivity of all modules | DalbirSingh Matharu | 2022-09-27 | 2022-10-04 | 1 | 100% | bar: WEEK 11 M to WEEK 12 F
2.3 | Integration of all modules and Report Writing | Sanskruti Chavan Janhavi Kasar | 2022-10-04 | 2022-10-11 | 1 | 100%
2.4 | Presentation II | Sanskruti Chavan Janhavi Kasar DalbirSingh Matharu Mayank Kumar | 2022-10-17 | 2022-10-21 | 2 | 100% | bar: WEEK 12 M to WEEK 14 F